## Product Backlog
Project Name | School Management And Reporting Tool (SMART)
Product Name: | School Management And Reporting Tool (SMART) | [6 empty] | Complete Fields in Green!!!
Team ID: | Bsg7347
| Team Member Name | [5 empty] | Initials | Student ID
Required | Biraj Singh GC | [5 empty] | BGC | 100867347
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 27 |  |  |  | Total | Total number of features (in column H)
1 | 23 | 4 |  |  | 1 | Total features left at the end of Sprint #1
2 | 17 | 6 |  |  | 2 | Total features left at the end of Sprint #2
3 | 12 | 5 |  |  | 3 | ...and so on
4 | 9 | 3
5 | 6 | 3
©2016-2021 by George F. Rice
This work is licensed under a Creative Commons Attribution 4.0 International License. | [6 empty] | Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Features
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a(n)… | I want to... | So that I can… | Notes
PERSON | 1 | 1 |  | 13 | 1 | Finished in Sprint 1 | Administrator | Track people’s names and email addresses | Find and contact them | Need a Person base class with to_string / operator<< name and a full_info method
STUDENT | 2 | 1 |  | 8 | 1 | Finished in Sprint 1 | Administrator | Track students by grade | Verify students’ progress | Need a Student derived class that includes the grade level (1-12)
PARENT | 3 | 1 |  | 3 | 1 | Finished in Sprint 1 | Administrator | Track parents | Coordinate on student progress | Need a Parent derived class
RELATE | 4 | 1 |  | 5 | 1 | Finished in Sprint 1 | Administrator | Associate each student with parents bidirectionally | Know which parents to contact | Mutual aggregate relationship
CLI | 5 | 1 | 25 | 13 | 1 | In Work | Administrator | Basic command line user interface | Verify the system before moving to a GUI | This is cli.cpp for sprint 1 only (optional for bonus points)
WINDOW | 6 | 2 |  | 13 | 2 | Finished in Sprint 2 | All | Use a windowed rather than command line interface | Use SMART more intuitively | Create a main window with a menu bar, data area, and status bar
D_STUDENT | 7 | 2 |  | 8 | 2 | Finished in Sprint 2 | Administrator | Create students via dialogs | Conveniently enter the data | Series of dialogs, one per constructor parameter, is OK
DISPLAY | 8 | 2 |  | 5 | 2 | Finished in Sprint 2 | Teacher | See all current data in the main window | Keep up with students | Display full_info for students and parents in a table in the data area
D_PARENT | 9 | 2 |  | 5 | 2 | Finished in Sprint 2 | Administrator | Create parents via dialogs | Conveniently enter the data | Series of dialogs, one per constructor parameter, is OK
D_RELATE | 10 | 2 |  | 8 | 2 | Finished in Sprint 2 | Administrator | Relate students to parents via dialogs | Conveniently enter the data | Dialog listing students and entering index, then same for parents
NEW | 11 | 2 |  | 2 | 2 | Finished in Sprint 2 | Administrator | Clear all data | Start a new school | Simply clear all elements from the vectors
SAVE | 12 | 3 |  | 13 | 3 | Finished in Sprint 3 | All | Write the data to persistent storage | Don’t have to re-enter data | See Lecture 15 for an object-oriented strategy to create the file format
LOAD | 13 | 3 |  | 8 | 3 | Finished in Sprint 3 | All | Load data for a school from persistent storage | Don’t have to re-enter data | Select file via a file chooser dialog
SAVEAS | 14 | 3 |  | 8 | 3 | Finished in Sprint 3 | Administrator | Save data to a different filename | Create backups or baselines for new schools | Select filename via a file chooser dialog
TOOLBAR | 15 | 3 |  | 5 | 3 | Finished in Sprint 3 | All | Use the major features via a toolbar | Point and click | Suggest using the Nim game’s toolbar as a baseline
ABOUT | 16 | 3 |  | 1 | 3 | Finished in Sprint 3 | Administrator | Display an About dialog with creator and version | Quickly determine which version is installed | Use Gtk::AboutDialog
COURSE | 17 | 4 |  | 21 | 4 | Finished in Sprint 4
SEMESTER | 18 | 4 |  | 8 | 4 | Finished in Sprint 4
SECTION | 19 | 4 |  | 5 | 4 | Finished in Sprint 4
20
21
22
SUBJECT | 23 | 5
TEACHER | 24 | 5 |  | 21
GRADE | 25 | 5 |  | 5
TRANSCRIPT | 26 | 5 |  | 8
ITERATORS | 27 | 5 |  | 8
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2021-03-02 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-09
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 10
Day 1 Left | 10 | 0
Day 2 Left | 10 | 0
Day 3 Left | 10 | 0
Day 4 Left | 10 | 0
Day 5 Left | 10 | 0
Day 6 Left | 10 | 0
Day 7 Left | 0 | 10
Note: Due to the late project start, the results of this sprint will be provided to you (although you may use your own solution if you prefer)
Task ID | Feature ID | Assigned To | Task | Status | Notes
1 | PERSON |  | Code person.h | Completed Day 7
2 | PERSON |  | Code person.cpp | Completed Day 7
3 | PERSON |  | Test compile Person class | Completed Day 7
4 | STUDENT |  | Code student.h | Completed Day 7
5 | STUDENT |  | Code student.cpp | Completed Day 7
6 | STUDENT |  | Test compile Student class | Completed Day 7
7 | PARENT |  | Duplicate Student to Parent | Completed Day 7
8 | PARENT |  | Remove grade, update to_string() and full_info() | Completed Day 7
9 | PARENT |  | Test compile Parent class | Completed Day 7
10 | RELATE |  | Build with example code and verify | Completed Day 7
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2021-03-09 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-23
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 11
Day 1 Left | 11 | 0
Day 2 Left | 11 | 0
Day 3 Left | 11 | 0
Day 4 Left | 11 | 0
Day 5 Left | 11 | 0
Day 6 Left | 11 | 0
Day 7 Left | 0 | 11
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | WINDOW |  | Baseline main.cpp from nim | Completed Day 7
2 | WINDOW |  | Update Makefile for gtkmm | Completed Day 7
3 | WINDOW |  | Baseline Mainwin class from nim | Completed Day 7
4 | D_STUDENT |  | Baseline EntryDialog class from Lecture 14 | Completed Day 7
5 | WINDOW |  | Create menu for SMART in Mainwin class | Completed Day 7
6 | DISPLAY |  | Add display label, vectors, and show_data method | Completed Day 7
7 | D_STUDENT |  | Write on_new_student_click using EntryDialog | Completed Day 7
8 | D_PARENT |  | Write on_new_parent_click using EntryDialog | Completed Day 7
9 | D_RELATE |  | Write on_student_parent_click using EntryDialog | Completed Day 7
10 | WINDOW |  | Refactor: select, select_student, and select_parent methods | Completed Day 7
11 | WINDOW |  | Test and improve error handling | Completed Day 7
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2021-03-23 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-30
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 15
Day 1 Left | 15 | 0
Day 2 Left | 15 | 0
Day 3 Left | 15 | 0
Day 4 Left | 15 | 0
Day 5 Left | 15 | 0
Day 6 Left | 15 | 0
Day 7 Left | 0 | 15
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | PERSON |  | SAVE AND LOAD IN PERSON | Completed Day 7
2 | STUDENT |  | SAVE AND LOAD IN PERSON | Completed Day 7
3 | PARENT |  | SAVE AND LOAD IN PERSON | Completed Day 7
4 | TOOLBAR |  | ADD New FILE in toolbar | Completed Day 7
5 | TOOLBAR |  | ADD LOAD FILE IN TOOL BAR | Completed Day 7
6 | TOOLBAR |  | ADD SAVE FILE IN TOOL BAR | Completed Day 7
7 | TOOLBAR |  | ADD SAVE AS IN TOOL BAR | Completed Day 7
8 | TOOLBAR |  | ADD NEW STUDENT IN TOOL BAR | Completed Day 7
9 | TOOLBAR |  | ADD NEW PARENT IN TOOL BAR | Completed Day 7
10 | TOOLBAR |  | ADD RELATION IN TOOLBAR | Completed Day 7
11 | WINDOW |  | CODE ONSAVECLICK | Completed Day 7
12 | WINDOW |  | CODE ONSAVEASCLICK | Completed Day 7
13 | WINDOW |  | CODE ONLOADCLICK | Completed Day 7
14 | WINDOW |  | ADD SAVE SAVEAS OPEN AND ABOUT IN MENUBAR | Completed Day 7
15 | WINDOW |  | CODE ABOUT | Completed Day 7
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2021-04-06 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-04-13
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 27
Day 1 Left | 27 | 0
Day 2 Left | 27 | 0
Day 3 Left | 27 | 0
Day 4 Left | 27 | 0
Day 5 Left | 27 | 0
Day 6 Left | 27 | 0
Day 7 Left | -3 | 30
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | SEMESTER |  | Write Semester enum | Completed Day 7
2 | SEMESTER |  | Implement operator<< | Completed Day 7
3 | SEMESTER |  | Implement load_semester | Completed Day 7
4 |  |  |  | Completed Day 7
5 | SUBJECT |  | Write Subject enum | Completed Day 7
6 | SUBJECT |  | Implement operator<< | Completed Day 7
7 | SUBJECT |  | Implement load_subject | Completed Day 7
8 | SUBJECT |  | Write subjects_vector (for iteration) | Completed Day 7
9
10 | COURSE |  | Write Course class | Completed Day 7
11 | COURSE |  | Implement operator<< | Completed Day 7
12 | COURSE |  | Implement Course::save | Completed Day 7
13 | COURSE |  | Implement Course::Course(ist) | Completed Day 7
14
15 | SECTION |  | Write Section class | Completed Day 7
16 | SECTION |  | Implement operator<< | Completed Day 7
17 | SECTION |  | Implement Section::save | Completed Day 7
18 | SECTION |  | Implement Section::Course(ist) | Completed Day 7
19 |  |  |  | Completed Day 7
20 | WINDOW |  | Mainwin: Add Insert > Course and Section | Completed Day 7
21 | WINDOW |  | Find new toolbar buttons and credit in Help > About | Completed Day 7
22 | WINDOW |  | Mainwin: Add toolbar buttons for Course and Section | Completed Day 7
23
24 | WINDOW |  | Mainwin: Add View > Students, Parents, Courses, Sections | Completed Day 7
25 | WINDOW |  | Add View enum and View parameter to show_data | Completed Day 7
26 | WINDOW |  | Add static current_view to show_data to remember view | Completed Day 7
27 | WINDOW |  | Update show_data to show different data types | Completed Day 7
28 |  |  |  | Completed Day 7
29 | WINDOW |  | Write Mainwin::on_new_course_click using EntryDialog | Completed Day 7
30 | WINDOW |  | Write Mainwin::on_new_section_click using EntryDialog | Completed Day 7
31
32 | WINDOW |  | Mainwin: Update on_save_click to save courses and sections | Completed Day 7
33 | WINDOW |  | Mainwin: Update on_open_click to load courses and sections | Completed Day 7
34 | WINDOW |  | Mainwin: Add logic to load v0.1 files (pre-courses/sections) | Completed Day 7
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2021-04-13 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-04-20
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84